## Dashboard
Production Control Sheet — Dasar AI & ML 2026/2027 |  |  | KPI | Value
Course | Dasar Kecerdasan Artifisial dan Pembelajaran Mesin |  | Overall Progress | 5.391%
Code | IF52510031 |  | Semester System Progress | 33.33%
Coverage | IF24A + IF24H |  | Delivered | 0
Control principle | Govern → Know → Learn → Prove → Compound |  | Ready / Published | 0
Current production focus | Week 4 — Pembagian Data, Validasi, Cross-Validation, Data Leakage |  | In Review | 6
|  |  | Not Started | 173
Week | Topic | Sub-CPMK | Progress
1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | 11.25%
2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | 11.25%
3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | 11.25%
4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | 5%
5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | 3.75%
6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | 3.75%
7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | 3.75%
8 | UTS | DAIML-Sub-CPMK102-1 | 5%
9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | 3.75%
10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | 3.75%
11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | 3.75%
12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | 3.75%
13 | Responsible AI | DAIML-Sub-CPMK082-1 | 3.75%
14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | 3.75%
15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | 3.75%
16 | UAS | DAIML-Sub-CPMK082-1 | 5%
Operating Rule: produce a complete weekly vertical slice; do not optimize slides in isolation.
Production Sequence
1 | Outcome / scope lock | → | 2 | Book / content lock
3 | Module + lecturer guide | → | 4 | Dataset / notebook / worksheet
5 | Assessment + rubric | → | 6 | Storyboard + slides
7 | LMS publish | → | 8 | Student evidence
9 | Post-class QA
Definition of Done | Accurate, aligned, executable, publishable, and traceable to evidence.
Next move | Finish Week 4 vertical slice, then backfill Week 1–3 to the same standard.

## Semester_Master
ID | Layer | Artifact | Definition of Done | Status | Priority | Owner | Target Date | Dependency | Output / Acceptance Criteria | File / URL | Notes | Status Score
SEM-01 | GOVERN | Curriculum / Source-of-Truth Audit | Curriculum identity, CPL/CPMK/BK and prerequisite alignment locked. | REVIEW | P0 — Now | Tri Aji |  |  | Kurikulum workbook reviewed and conflicts recorded. |  | Review against latest workbook. | 0.5
SEM-02 | GOVERN | RPS Final | RPS identities, outcomes, weekly map, assessment, bibliography consistent. | REVIEW | P0 — Now | Tri Aji |  | SEM-01 | RPS signed/ready as authoritative semester contract. | https://docs.google.com/document/d/1jfaenJg9Oi6PEsMjASpqO1D90EcQyd5H/edit | Current RPS exists; final QA needed. | 0.5
SEM-03 | GOVERN | RTM Master | All weekly assignments/assessments mapped to RPS and operational. | REVIEW | P0 — Now | Tri Aji |  | SEM-02 | RTM instructions + outputs + rubrics are executable. | https://docs.google.com/document/d/1ktAxiyG_ctP2Ql8Svx8RBbl370c8wPia/edit | Current RTM exists; QA and production links needed. | 0.5
SEM-04 | GOVERN | Assessment Blueprint | Assessment coverage, weights, cognitive level, evidence and traceability mapped. | DRAFT | P1 — Next | Tri Aji |  | SEM-02, SEM-03 | One semester assessment blueprint approved. |  | RPS already gives weights; convert into explicit blueprint. | 0.25
SEM-05 | LEARN | Semester Learning Architecture | End-to-end learning spine, dependencies, WHY/WHAT/HOW progression. | REVIEW | P0 — Now | Tri Aji |  | SEM-02 | All weeks form one coherent learning journey. |  | Topic spine exists in RPS; pedagogical audit needed. | 0.5
SEM-06 | KNOW | Book Table of Contents | 14 learning chapters + exam/project integration mapped to weekly outcomes. | NOT STARTED | P1 — Next | Tri Aji |  | SEM-05 | TOC locked before chapter-by-chapter production. |  | Use rolling book development. | 0
SEM-07 | PROVE | Project Architecture | W12–15 project stages, evidence, repo/report/demo, responsible AI and reproducibility. | DRAFT | P2 — Planned | Tri Aji |  | SEM-03 | Project brief, stage gates, rubric and submission flow locked. |  | RPS defines proposal → responsible AI → pipeline → final demo. | 0.25
SEM-08 | LEARN | LMS Course Skeleton | Weekly sections, naming, content pattern, submission pattern and links standardized. | NOT STARTED | P1 — Next | TBD |  | SEM-05 | All 16 weeks have standard LMS shells. |  | Can be implemented progressively. | 0
SEM-09 | PROVE | Mastery Tracker | Outcome-level mastery beyond attendance/grades, with remediation flags. | NOT STARTED | P2 — Planned | TBD |  | SEM-04 | Students can be tracked by mastery dimension and evidence. |  | Separate from existing attendance/grade trackers. | 0
SEM-10 | PROVE | Question Bank | Tagged question bank by week, concept, level, difficulty and answer/rubric. | NOT STARTED | P2 — Planned | TBD |  | SEM-04 | Reusable bank ready for quizzes, UTS, UAS and practice. |  | Build continuously from weekly packages. | 0
SEM-11 | COMPOUND | Teaching Package Visual & Prompt OS | Standard for content, storyboard, slides, visuals, learning action and QA. | READY | P0 — Now | Tri Aji |  | SEM-05 | Master prompt package version-controlled and reusable. |  | Master Prompt Package Mata Kuliah v2 prepared. | 0.75
SEM-12 | COMPOUND | Production Control Sheet | Single command center for semester and weekly package production. | READY | P0 — Now | Tri Aji |  | SEM-01 | Dashboard, backlog, status lifecycle, sources and QA controls operational. |  | This workbook. | 0.75

## Production_Backlog
Item ID | Week | Topic | Sub-CPMK | Layer | Artifact | Weight | Status | Priority | Owner | Dependency | Target Date | Output / Definition of Done | File / URL | QA Gate | Status Score | Weighted Score | Notes
W01-BOOK | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | KNOW | Book Chapter | 10 | NOT STARTED | P1 — Next | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W01-MOD | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | LEARN | Student Module | 8 | NOT STARTED | P1 — Next | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W01-GUIDE | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P1 — Next | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W01-STORY | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | LEARN | Storyboard | 5 | REVIEW | P1 — Next | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0.5 | 2.5 | Existing Week 1–3 material exists; needs audit against current Teaching Package OS.
W01-SLIDE | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | LEARN | Slides | 10 | REVIEW | P1 — Next | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0.5 | 5 | Existing Week 1–3 material exists; needs audit against current Teaching Package OS.
W01-DATA | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P1 — Next | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W01-LAB | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P1 — Next | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W01-WORK | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P1 — Next | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W01-AIP | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P1 — Next | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W01-ASSESS | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P1 — Next | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-01 already specified in RPS/RTM; production file still needs finalization.
W01-RUBRIC | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P1 — Next | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-01 already specified in RPS/RTM; production file still needs finalization.
W01-LMS | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | LEARN | LMS Package | 5 | NOT STARTED | P1 — Next | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W01-EVID | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P1 — Next | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W01-QA | 1 | Pengantar AI dan Machine Learning | DAIML-Sub-CPMK082-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P1 — Next | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W02-BOOK | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | KNOW | Book Chapter | 10 | NOT STARTED | P1 — Next | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W02-MOD | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | LEARN | Student Module | 8 | NOT STARTED | P1 — Next | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W02-GUIDE | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P1 — Next | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W02-STORY | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | LEARN | Storyboard | 5 | REVIEW | P1 — Next | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0.5 | 2.5 | Existing Week 1–3 material exists; needs audit against current Teaching Package OS.
W02-SLIDE | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | LEARN | Slides | 10 | REVIEW | P1 — Next | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0.5 | 5 | Existing Week 1–3 material exists; needs audit against current Teaching Package OS.
W02-DATA | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P1 — Next | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W02-LAB | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P1 — Next | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W02-WORK | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P1 — Next | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W02-AIP | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P1 — Next | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W02-ASSESS | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P1 — Next | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-02 already specified in RPS/RTM; production file still needs finalization.
W02-RUBRIC | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P1 — Next | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-02 already specified in RPS/RTM; production file still needs finalization.
W02-LMS | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | LEARN | LMS Package | 5 | NOT STARTED | P1 — Next | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W02-EVID | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P1 — Next | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W02-QA | 2 | Eksplorasi Data untuk ML | DAIML-Sub-CPMK102-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P1 — Next | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W03-BOOK | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | KNOW | Book Chapter | 10 | NOT STARTED | P1 — Next | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W03-MOD | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | LEARN | Student Module | 8 | NOT STARTED | P1 — Next | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W03-GUIDE | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P1 — Next | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W03-STORY | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | LEARN | Storyboard | 5 | REVIEW | P1 — Next | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0.5 | 2.5 | Existing Week 1–3 material exists; needs audit against current Teaching Package OS.
W03-SLIDE | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | LEARN | Slides | 10 | REVIEW | P1 — Next | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0.5 | 5 | Existing Week 1–3 material exists; needs audit against current Teaching Package OS.
W03-DATA | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P1 — Next | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W03-LAB | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P1 — Next | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W03-WORK | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P1 — Next | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W03-AIP | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P1 — Next | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W03-ASSESS | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P1 — Next | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-03 already specified in RPS/RTM; production file still needs finalization.
W03-RUBRIC | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P1 — Next | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-03 already specified in RPS/RTM; production file still needs finalization.
W03-LMS | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | LEARN | LMS Package | 5 | NOT STARTED | P1 — Next | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W03-EVID | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P1 — Next | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W03-QA | 3 | Preprocessing dan Feature Engineering | DAIML-Sub-CPMK102-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P1 — Next | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-BOOK | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | KNOW | Book Chapter | 10 | NOT STARTED | P0 — Now | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-MOD | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | LEARN | Student Module | 8 | NOT STARTED | P0 — Now | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-GUIDE | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P0 — Now | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-STORY | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | LEARN | Storyboard | 5 | DRAFT | P0 — Now | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.25 | 20-slide storyboard drafted 7 Oct 2026: Validation Before Believing.
W04-SLIDE | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | LEARN | Slides | 10 | NOT STARTED | P0 — Now | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-DATA | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P0 — Now | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-LAB | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P0 — Now | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-WORK | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P0 — Now | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-AIP | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P0 — Now | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-ASSESS | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P0 — Now | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-04 scope and weighting defined; actual Moodle quiz/key still to produce.
W04-RUBRIC | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P0 — Now | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-04 scope and weighting defined; actual Moodle quiz/key still to produce.
W04-LMS | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | LEARN | LMS Package | 5 | NOT STARTED | P0 — Now | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-EVID | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P0 — Now | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W04-QA | 4 | Pembagian Data dan Validasi | DAIML-Sub-CPMK102-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P0 — Now | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-BOOK | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | KNOW | Book Chapter | 10 | NOT STARTED | P1 — Next | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-MOD | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | LEARN | Student Module | 8 | NOT STARTED | P1 — Next | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-GUIDE | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P1 — Next | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-STORY | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | LEARN | Storyboard | 5 | NOT STARTED | P1 — Next | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-SLIDE | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | LEARN | Slides | 10 | NOT STARTED | P1 — Next | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-DATA | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P1 — Next | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-LAB | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P1 — Next | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-WORK | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P1 — Next | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-AIP | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P1 — Next | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-ASSESS | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P1 — Next | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-05 already specified in RPS/RTM; production file still needs finalization.
W05-RUBRIC | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P1 — Next | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-05 already specified in RPS/RTM; production file still needs finalization.
W05-LMS | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | LEARN | LMS Package | 5 | NOT STARTED | P1 — Next | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-EVID | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P1 — Next | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W05-QA | 5 | Klasifikasi I: KNN dan Decision Tree | DAIML-Sub-CPMK082-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P1 — Next | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-BOOK | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | KNOW | Book Chapter | 10 | NOT STARTED | P2 — Planned | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-MOD | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | LEARN | Student Module | 8 | NOT STARTED | P2 — Planned | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-GUIDE | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P2 — Planned | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-STORY | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | LEARN | Storyboard | 5 | NOT STARTED | P2 — Planned | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-SLIDE | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | LEARN | Slides | 10 | NOT STARTED | P2 — Planned | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-DATA | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P2 — Planned | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-LAB | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P2 — Planned | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-WORK | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P2 — Planned | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-AIP | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P2 — Planned | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-ASSESS | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P2 — Planned | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-06 already specified in RPS/RTM; production file still needs finalization.
W06-RUBRIC | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P2 — Planned | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-06 already specified in RPS/RTM; production file still needs finalization.
W06-LMS | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | LEARN | LMS Package | 5 | NOT STARTED | P2 — Planned | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-EVID | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P2 — Planned | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W06-QA | 6 | Regresi Linear dan Metrik Evaluasi | DAIML-Sub-CPMK102-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P2 — Planned | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-BOOK | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | KNOW | Book Chapter | 10 | NOT STARTED | P2 — Planned | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-MOD | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | LEARN | Student Module | 8 | NOT STARTED | P2 — Planned | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-GUIDE | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P2 — Planned | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-STORY | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | LEARN | Storyboard | 5 | NOT STARTED | P2 — Planned | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-SLIDE | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | LEARN | Slides | 10 | NOT STARTED | P2 — Planned | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-DATA | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P2 — Planned | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-LAB | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P2 — Planned | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-WORK | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P2 — Planned | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-AIP | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P2 — Planned | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-ASSESS | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P2 — Planned | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-07 already specified in RPS/RTM; production file still needs finalization.
W07-RUBRIC | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P2 — Planned | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-07 already specified in RPS/RTM; production file still needs finalization.
W07-LMS | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | LEARN | LMS Package | 5 | NOT STARTED | P2 — Planned | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-EVID | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P2 — Planned | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W07-QA | 7 | Clustering dan Metrik Clustering | DAIML-Sub-CPMK102-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P2 — Planned | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
UTS-BLUEPRINT | 8 | UTS | DAIML-Sub-CPMK102-1 | PROVE | Exam Blueprint | 20 | DRAFT | P2 — Planned | TBD | RPS + Assessment Blueprint |  | Coverage, indikator, level kognitif, proporsi, dan traceability ke CPMK. |  | Accuracy + alignment + clarity + usability | 0.25 | 5 | Coverage already defined in RPS; explicit blueprint still needs production.
UTS-QUESTION | 8 | UTS | DAIML-Sub-CPMK102-1 | PROVE | Question Set | 25 | NOT STARTED | P2 — Planned | TBD | Exam Blueprint |  | Soal final lengkap, jelas, dan seimbang. |  | Accuracy + alignment + clarity + usability | 0 | 0
UTS-KEY | 8 | UTS | DAIML-Sub-CPMK102-1 | PROVE | Answer Key / Rubric | 20 | NOT STARTED | P2 — Planned | TBD | Question Set |  | Kunci/rubrik lengkap dan dapat dipakai konsisten. |  | Accuracy + alignment + clarity + usability | 0 | 0
UTS-INSTR | 8 | UTS | DAIML-Sub-CPMK102-1 | LEARN | Exam Instruction | 10 | NOT STARTED | P2 — Planned | TBD | Exam Blueprint |  | Instruksi teknis-akademik yang jelas untuk mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
UTS-LMS | 8 | UTS | DAIML-Sub-CPMK102-1 | LEARN | LMS Exam Package | 10 | NOT STARTED | P2 — Planned | TBD | Question Set + Instruction |  | Setup LMS, file, waktu, submission, dan komunikasi. |  | Accuracy + alignment + clarity + usability | 0 | 0
UTS-EVID | 8 | UTS | DAIML-Sub-CPMK102-1 | PROVE | Exam Evidence Archive | 5 | NOT STARTED | P2 — Planned | TBD | Delivered exam |  | Bukti pelaksanaan dan arsip asesmen tertata. |  | Accuracy + alignment + clarity + usability | 0 | 0
UTS-QA | 8 | UTS | DAIML-Sub-CPMK102-1 | COMPOUND | Post-Exam Analysis | 10 | NOT STARTED | P2 — Planned | TBD | Exam results + evidence |  | Analisis item/hasil, gap mastery, dan tindakan perbaikan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-BOOK | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | KNOW | Book Chapter | 10 | NOT STARTED | P3 — Later | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-MOD | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | LEARN | Student Module | 8 | NOT STARTED | P3 — Later | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-GUIDE | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P3 — Later | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-STORY | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | LEARN | Storyboard | 5 | NOT STARTED | P3 — Later | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-SLIDE | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | LEARN | Slides | 10 | NOT STARTED | P3 — Later | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-DATA | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P3 — Later | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-LAB | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P3 — Later | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-WORK | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P3 — Later | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-AIP | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P3 — Later | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-ASSESS | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P3 — Later | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-08 already specified in RPS/RTM; production file still needs finalization.
W09-RUBRIC | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P3 — Later | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-08 already specified in RPS/RTM; production file still needs finalization.
W09-LMS | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | LEARN | LMS Package | 5 | NOT STARTED | P3 — Later | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-EVID | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P3 — Later | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W09-QA | 9 | Klasifikasi II dan Model Selection | DAIML-Sub-CPMK082-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P3 — Later | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-BOOK | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | KNOW | Book Chapter | 10 | NOT STARTED | P3 — Later | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-MOD | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | LEARN | Student Module | 8 | NOT STARTED | P3 — Later | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-GUIDE | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P3 — Later | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-STORY | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | LEARN | Storyboard | 5 | NOT STARTED | P3 — Later | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-SLIDE | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | LEARN | Slides | 10 | NOT STARTED | P3 — Later | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-DATA | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P3 — Later | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-LAB | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P3 — Later | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-WORK | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P3 — Later | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-AIP | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P3 — Later | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-ASSESS | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P3 — Later | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-09 already specified in RPS/RTM; production file still needs finalization.
W10-RUBRIC | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P3 — Later | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-09 already specified in RPS/RTM; production file still needs finalization.
W10-LMS | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | LEARN | LMS Package | 5 | NOT STARTED | P3 — Later | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-EVID | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P3 — Later | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W10-QA | 10 | Generalisasi, Overfitting, dan Regularisasi | DAIML-Sub-CPMK082-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P3 — Later | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-BOOK | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | KNOW | Book Chapter | 10 | NOT STARTED | P3 — Later | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-MOD | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | LEARN | Student Module | 8 | NOT STARTED | P3 — Later | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-GUIDE | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P3 — Later | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-STORY | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | LEARN | Storyboard | 5 | NOT STARTED | P3 — Later | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-SLIDE | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | LEARN | Slides | 10 | NOT STARTED | P3 — Later | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-DATA | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P3 — Later | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-LAB | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P3 — Later | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-WORK | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P3 — Later | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-AIP | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P3 — Later | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-ASSESS | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P3 — Later | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-10 already specified in RPS/RTM; production file still needs finalization.
W11-RUBRIC | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P3 — Later | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-10 already specified in RPS/RTM; production file still needs finalization.
W11-LMS | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | LEARN | LMS Package | 5 | NOT STARTED | P3 — Later | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-EVID | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P3 — Later | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W11-QA | 11 | Jaringan Syaraf Tiruan | DAIML-Sub-CPMK082-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P3 — Later | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-BOOK | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | KNOW | Book Chapter | 10 | NOT STARTED | P3 — Later | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-MOD | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | LEARN | Student Module | 8 | NOT STARTED | P3 — Later | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-GUIDE | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P3 — Later | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-STORY | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | LEARN | Storyboard | 5 | NOT STARTED | P3 — Later | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-SLIDE | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | LEARN | Slides | 10 | NOT STARTED | P3 — Later | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-DATA | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P3 — Later | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-LAB | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P3 — Later | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-WORK | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P3 — Later | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-AIP | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P3 — Later | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-ASSESS | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P3 — Later | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-11 already specified in RPS/RTM; production file still needs finalization.
W12-RUBRIC | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P3 — Later | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-11 already specified in RPS/RTM; production file still needs finalization.
W12-LMS | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | LEARN | LMS Package | 5 | NOT STARTED | P3 — Later | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-EVID | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P3 — Later | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W12-QA | 12 | Pengantar Deep Learning dan Generative AI | DAIML-Sub-CPMK082-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P3 — Later | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-BOOK | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | KNOW | Book Chapter | 10 | NOT STARTED | P3 — Later | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-MOD | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | LEARN | Student Module | 8 | NOT STARTED | P3 — Later | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-GUIDE | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P3 — Later | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-STORY | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | LEARN | Storyboard | 5 | NOT STARTED | P3 — Later | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-SLIDE | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | LEARN | Slides | 10 | NOT STARTED | P3 — Later | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-DATA | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P3 — Later | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-LAB | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P3 — Later | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-WORK | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P3 — Later | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-AIP | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P3 — Later | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-ASSESS | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P3 — Later | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-12 already specified in RPS/RTM; production file still needs finalization.
W13-RUBRIC | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P3 — Later | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-12 already specified in RPS/RTM; production file still needs finalization.
W13-LMS | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | LEARN | LMS Package | 5 | NOT STARTED | P3 — Later | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-EVID | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P3 — Later | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W13-QA | 13 | Responsible AI | DAIML-Sub-CPMK082-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P3 — Later | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-BOOK | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | KNOW | Book Chapter | 10 | NOT STARTED | P3 — Later | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-MOD | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | LEARN | Student Module | 8 | NOT STARTED | P3 — Later | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-GUIDE | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P3 — Later | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-STORY | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | LEARN | Storyboard | 5 | NOT STARTED | P3 — Later | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-SLIDE | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | LEARN | Slides | 10 | NOT STARTED | P3 — Later | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-DATA | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P3 — Later | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-LAB | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P3 — Later | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-WORK | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P3 — Later | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-AIP | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P3 — Later | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-ASSESS | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P3 — Later | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-13 already specified in RPS/RTM; production file still needs finalization.
W14-RUBRIC | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P3 — Later | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-13 already specified in RPS/RTM; production file still needs finalization.
W14-LMS | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | LEARN | LMS Package | 5 | NOT STARTED | P3 — Later | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-EVID | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P3 — Later | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W14-QA | 14 | Pipeline ML End-to-End dan Reproduksibilitas | DAIML-Sub-CPMK082-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P3 — Later | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-BOOK | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | KNOW | Book Chapter | 10 | NOT STARTED | P3 — Later | TBD | Semester learning map + book TOC |  | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-MOD | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | LEARN | Student Module | 8 | NOT STARTED | P3 — Later | TBD | Book Chapter |  | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-GUIDE | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | LEARN | Lecturer Guide | 6 | NOT STARTED | P3 — Later | TBD | Student Module |  | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-STORY | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | LEARN | Storyboard | 5 | NOT STARTED | P3 — Later | TBD | Book Chapter + Lecturer Guide |  | Storyline slide lengkap dan audited sebelum visual final. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-SLIDE | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | LEARN | Slides | 10 | NOT STARTED | P3 — Later | TBD | Storyboard |  | Deck final presentation-ready dan take-home friendly. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-DATA | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | LEARN | Dataset / Case | 6 | NOT STARTED | P3 — Later | TBD | RPS topic + case requirement |  | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-LAB | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | LEARN | Notebook / Lab | 10 | NOT STARTED | P3 — Later | TBD | Dataset / Case + Book Chapter |  | Starter + solution notebook dapat dijalankan/reproduksi. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-WORK | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | LEARN | Worksheet / Practice | 7 | NOT STARTED | P3 — Later | TBD | Book Chapter + Student Module |  | Latihan aktif yang menghasilkan reasoning/output mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-AIP | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | LEARN | AI Learning Prompts | 3 | NOT STARTED | P3 — Later | TBD | Book Chapter + Worksheet |  | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-ASSESS | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | PROVE | Assignment / Quiz | 8 | DRAFT | P3 — Later | TBD | RTM + outcome |  | Instruksi asesmen executable dan aligned ke outcome. |  | Accuracy + alignment + clarity + usability | 0.25 | 2 | T-14 already specified in RPS/RTM; production file still needs finalization.
W15-RUBRIC | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | PROVE | Rubric / Answer Key | 7 | DRAFT | P3 — Later | TBD | Assignment / Quiz |  | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai. |  | Accuracy + alignment + clarity + usability | 0.25 | 1.75 | T-14 already specified in RPS/RTM; production file still needs finalization.
W15-LMS | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | LEARN | LMS Package | 5 | NOT STARTED | P3 — Later | TBD | Module + Slides + Assessment |  | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-EVID | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | PROVE | Evidence / Student Artifact | 8 | NOT STARTED | P3 — Later | TBD | Assignment / Practice |  | Bukti mastery yang jelas: notebook/report/video/demo/dll. |  | Accuracy + alignment + clarity + usability | 0 | 0
W15-QA | 15 | Presentasi Proyek Akhir | DAIML-Sub-CPMK082-1 | COMPOUND | Post-Class QA | 7 | NOT STARTED | P3 — Later | TBD | Delivered class + student evidence |  | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi. |  | Accuracy + alignment + clarity + usability | 0 | 0
UAS-BLUEPRINT | 16 | UAS | DAIML-Sub-CPMK082-1 | PROVE | Exam Blueprint | 20 | DRAFT | P3 — Later | TBD | RPS + Assessment Blueprint |  | Coverage, indikator, level kognitif, proporsi, dan traceability ke CPMK. |  | Accuracy + alignment + clarity + usability | 0.25 | 5 | Coverage already defined in RPS; explicit blueprint still needs production.
UAS-QUESTION | 16 | UAS | DAIML-Sub-CPMK082-1 | PROVE | Question Set | 25 | NOT STARTED | P3 — Later | TBD | Exam Blueprint |  | Soal final lengkap, jelas, dan seimbang. |  | Accuracy + alignment + clarity + usability | 0 | 0
UAS-KEY | 16 | UAS | DAIML-Sub-CPMK082-1 | PROVE | Answer Key / Rubric | 20 | NOT STARTED | P3 — Later | TBD | Question Set |  | Kunci/rubrik lengkap dan dapat dipakai konsisten. |  | Accuracy + alignment + clarity + usability | 0 | 0
UAS-INSTR | 16 | UAS | DAIML-Sub-CPMK082-1 | LEARN | Exam Instruction | 10 | NOT STARTED | P3 — Later | TBD | Exam Blueprint |  | Instruksi teknis-akademik yang jelas untuk mahasiswa. |  | Accuracy + alignment + clarity + usability | 0 | 0
UAS-LMS | 16 | UAS | DAIML-Sub-CPMK082-1 | LEARN | LMS Exam Package | 10 | NOT STARTED | P3 — Later | TBD | Question Set + Instruction |  | Setup LMS, file, waktu, submission, dan komunikasi. |  | Accuracy + alignment + clarity + usability | 0 | 0
UAS-EVID | 16 | UAS | DAIML-Sub-CPMK082-1 | PROVE | Exam Evidence Archive | 5 | NOT STARTED | P3 — Later | TBD | Delivered exam |  | Bukti pelaksanaan dan arsip asesmen tertata. |  | Accuracy + alignment + clarity + usability | 0 | 0
UAS-QA | 16 | UAS | DAIML-Sub-CPMK082-1 | COMPOUND | Post-Exam Analysis | 10 | NOT STARTED | P3 — Later | TBD | Exam results + evidence |  | Analisis item/hasil, gap mastery, dan tindakan perbaikan. |  | Accuracy + alignment + clarity + usability | 0 | 0

## Definitions
Status | Score | Meaning | Priority | Meaning | Layer | Artifact | Weight | Definition of Done
NOT STARTED | 0% | Belum mulai. | P0 — Now | Kerjakan sekarang / current bottleneck. | KNOW | Book Chapter | 10 | Bab kanonik: konsep, intuisi, istilah, contoh, common mistakes, rangkuman.
DRAFT | 25% | Sudah ada draft awal. | P1 — Next | Berikutnya setelah P0. | LEARN | Student Module | 8 | Tujuan, prerequisite, alur belajar, aktivitas, practice, tugas, refleksi.
REVIEW | 50% | Sedang/siap ditinjau untuk akurasi dan alignment. | P2 — Planned | Perlu disiapkan dalam horizon dekat. | LEARN | Lecturer Guide | 6 | Timing, hook, analogi, pertanyaan Socratic, demo, transisi, debrief.
READY | 75% | Secara substansi siap dipakai; final publishing belum selesai. | P3 — Later | Belum mendesak; jaga visibility. | LEARN | Storyboard | 5 | Storyline slide lengkap dan audited sebelum visual final.
PUBLISHED | 90% | Sudah dipublikasikan/diunggah untuk mahasiswa. |  |  | LEARN | Slides | 10 | Deck final presentation-ready dan take-home friendly.
DELIVERED | 100% | Sudah digunakan/dilaksanakan. |  |  | LEARN | Dataset / Case | 6 | Dataset/kasus valid, data dictionary/source, dan konteks penggunaan.
IMPROVE | 85% | Sudah digunakan namun perlu perbaikan pada iterasi berikut. |  |  | LEARN | Notebook / Lab | 10 | Starter + solution notebook dapat dijalankan/reproduksi.
[5 empty] | LEARN | Worksheet / Practice | 7 | Latihan aktif yang menghasilkan reasoning/output mahasiswa.
[5 empty] | LEARN | AI Learning Prompts | 3 | Prompt tutor/critic/checker yang membantu tanpa menggantikan berpikir.
[5 empty] | PROVE | Assignment / Quiz | 8 | Instruksi asesmen executable dan aligned ke outcome.
[5 empty] | PROVE | Rubric / Answer Key | 7 | Rubrik/kunci jelas, konsisten, dan dapat dipakai menilai.
[5 empty] | LEARN | LMS Package | 5 | Materi, instruksi, link/file, forum/quiz/upload tertata di LMS.
[5 empty] | PROVE | Evidence / Student Artifact | 8 | Bukti mastery yang jelas: notebook/report/video/demo/dll.
[5 empty] | COMPOUND | Post-Class QA | 7 | KEEP/FIX/ADD/REMOVE + bukti kesulitan mahasiswa + revisi.

## Sources
ID | Source | Role | URL | Notes
S01 | Kurikulum OBE IF 2025 — Revisi 2026 | Primary curriculum source of truth | https://docs.google.com/spreadsheets/d/14frRyWdgLshOJ-5hVcL2CCoxCtm0d5gc | Use for CPL/CPMK/BK/course identity.
S02 | RPS_RTM_Dasar_Kecerdasan_Artifisial_dan_Pembelajaran_Mesin_2026-2027 | Operational RPS/RTM — IF24A | https://docs.google.com/document/d/1jfaenJg9Oi6PEsMjASpqO1D90EcQyd5H/edit | Current weekly topic, assessment, and RTM basis.
S03 | RTM_Dasar_Kecerdasan_Artifisial_dan_Pembelajaran_Mesin_IF24A-IF24H_2026_Template_Resmi_UAI | RTM source — IF24A | https://docs.google.com/document/d/1ktAxiyG_ctP2Ql8Svx8RBbl370c8wPia/edit | Detailed task structure.
S04 | IF24A - Dasar AI & ML - Tracker Presensi, Tugas dan Nilai | Class delivery tracker | https://docs.google.com/spreadsheets/d/1N9HH-Pk2Dbg2NnV5w0mGIld2PDibdIz16H9GpBUDluI/edit | Operational class evidence.
S05 | IF24H - Dasar AI & ML - Tracker Presensi, Tugas dan Nilai | Hybrid class delivery tracker | https://docs.google.com/spreadsheets/d/1WBP9NIduXQ_xqiB_PorhJKzB1eryTcrKeG8fRO0L3RI/edit | Operational hybrid-class evidence.
S06 | Master Prompt Package Mata Kuliah v2 | Teaching Package Operating System |  | Local master prompt created 7 Oct 2026; upload/link when finalized.